	[image: image1.png]@0 BRITISH
®©® COUNCIL




Consultancy 
Terms of Reference

	Role Title

	Monitoring, Evaluation and Learning (MEL) - Local Expert 

	Role Information

	Role Type
	 Location
	 Duration
	 Reports to:

	Consultancy
	Libya/  Home-based 
	100 Days 
	MEL Senior Expert

	Project Background

	The EU funded project “EU Libya Technical and Vocational Education and Training (TVET) Delivery and Development” originally started in January 2013 and was suspended on the grounds of “force majeure” in October 2014. The project has now re-launched and is remotely managed from Tunis with visits to Libya from some project staff as required.

The purpose of the project is to improve capacity and provide quality technical and vocational education and training in Libya, and to improve the quality of content and relevance of education and training to meet demands in the labour market. The reactivated implementation will continue to develop capacity and methodologies for the TVET offer in Libya in line with real demand for skills in the Libyan economy. It will also focus on supporting the establishment of Centres of Excellence in a limited number of TVET institutions. Activities in these Centres of Excellence will include:

· Capacity building in leadership and management 

· Raising the skill levels of teachers
· Providing relevant advice and guidance to graduates and the unemployed 

· Improving collaboration and understanding between education and business. 
As a result, the Centre of Excellence institutes will be better equipped to provide higher quality training that is more relevant and matched to the needs of local employment.
Overall Result Areas of the programme are as follows: 

· Result Area A: Enhance the quality and relevance of training provision in a selected number of TVE schools to meet the social and economic needs of the community (Centres of Excellence)

· Result Area B: Reinforce capacity of the main stakeholders representing the demand side such as employers’ organisations, syndicates and others to play an active role in the modernisation of the TVE system

· Result Area C: Dissemination of project success and lessons learned informs wider initiatives at a national level and provides resources for further development of Centres of Excellence in additional municipalities.

	Purpose of the consultancy

	Based on a comprehensive Monitoring, Evaluation and Learning (MEL) framework, the purpose of this consultancy is to ensure a consistent approach to perform continuous monitoring and evaluation by the selected Expert. This will ensure tracking of the project’s achievements and provide critical information for the steering of project activities. It will also form all types of reporting and work planning of the project, for the benefit of the Project’s management, partners and stakeholders. 

Under the technical guidance of the Senior MEL expert and Team Leader- KE1, the Expert will be based in Libya and will be recruited (initially) for a period of 100 working days to support the implementation of the MEL framework and will be reporting to the Senior MEL expert. In so doing, the expert will ensure compliance with contractual obligations as detailed in the Organisation & Methodology (5/2019) and will enable the key partners, notably Ministries, project working groups, businesses and associations to actively and adequately monitor the implementation of all activities foreseen under the project’s workplan. 
The successful candidate will work closely with the Senior MEL expert, Team Leader, the Project Team, and other Key & Non-Key Experts. The consultancy will be spread over 12 months starting February 2021.

	Scope of works:

	M&E Framework and Capacity Development
· Review existing project documents, including the logical framework, workplan and identify critical information gaps from existing data. 
· Support the Senior MEL expert in establishing Key Impact Indicators (KIIs) for the project duration, including data collection, analysis, and reporting tools.

· Ensure that project indicators are SMART with clear definitions, milestones, data collection strategies and frequency of collection, and finalised through a participatory stakeholder workshop/webinar. This workshop should serve as a capacity development exercise for key stakeholders. 
· Support the Senior MEL expert in the development of a risk-mitigation strategy aligned with the MEL framework.
Monitoring and Reporting 

· Contribute to the production of MEL reports and the dissemination of results to the Project Management Team, highlighting achievements and challenges and suggesting measures targeting achievement of delivery of project indicators. 
· Ensure effective data collection as per the Senior MEL expert’s instructions.
· Facilitate a project closure workshop and support the Senior MEL expert in producing an impact analysis based on the MEL baseline assessment/ project workplan 

· Support reporting systems, notably the inception report, six-monthly MEL reports, and a final technical report, in collaboration with the Senior M&E expert. 
· Conduct field monitoring visits, ensuring preparation and submission of systematic monitoring reports. 


	Expected Deliverables

	· Support to the development of user-friendly and result-based standardised templates and reporting tools for data collection and analysis
· Support to the development of a detailed action plan with timeline and reporting milestones for the consultancy period
· Comprehensive field visits reports, including summaries of interviews/discussions, analysis of available monitoring data, and identification of key issues and learning
· Support to the development of a database of local stakeholders 



	Skills and Competencies   

	Qualification and skills:

· Hold a university degree in a relevant field (social sciences, incl. economics, statistics, communication) at Masters level

· A minimum of 3 years of general professional experience working on project MEL including the development and implementation of MEL plans and methodologies
· Strong analytical, reporting and communication skills
· Language competency (professional level) in English and Arabic 

· Conversant in MS office applications and graphic illustrations


	

	Contract details

	The assignment is offered on a fixed- term basis for 100 working days in total, spread over a 12 month- period. This assignment is essentially home-based but requires engaging in frequent field visits to different regions in Libya, subject to applicable travel restrictions.
A competitive fee in line with large donor funded programmes is offered. This will be agreed once the successful candidate is identified and will be commensurate with the successful candidate’s previous experience. 



	To apply

	If you are interested in this vacancy, kindly submit your application by February 24th, 2021. 
Your Application should include the following:

1. Your CV

2. A supporting statement highlighting how your experience and skills match the requirements of the assignment

Applications should be submitted by email to HRlibya@ly.britishcouncil.org   
Please note that only short-listed candidates will be contacted.



